## Eng. Wael
Issue Description | Status | Rabab Comment | Customer Comment | Assigned to
The language button is very confusing to me , can it be just English/عربي with a combo box, the earth sign with E and ع was a bit confusing | Fixed | the button is bigger now, and includes the English/عربي words, not just confused letters |  | UI
List of prices to be in this format 200$-300$ | Not Started | will check |  | Gouda
Online Second Opinions in the logo, Opinion without ”S” | Fixed | will check |  | UI
The” Y” in “Your” Medical Consultant in the logo is not clear, is there a way to make it clear as it can be read “Our Medical Consultant” | CR | As per the design this was the logo approved and if you want to change, it will be considered as CR | Closed as agreed
In the Why YMC part, the 3 icons at the right side are clickable, will they include a subtext explanation when we click them ? because when I click them it takes me to the home screen not a special window for their explanation | Missing Content | Anything that is redirected to homepage is waiting for a content from your side, so this will be a link to inner page with a content or files or something, we need you to update us with the data |  | Deffered
The “important facts” beside “featured doctors” makes both related to each other, Can we add YMC before important facts so it appears as general facts |  | As per the design approved, can`t be changed now as this will impact the whole homepage design | we will hide the whole control featured doctors and important facts | Gouda | hide whole section
Important facts are counting a bit slow, I have to wait till they finish, whether we make them fixed or count faster | Not Started | will check | It will be hidden | Gouda | hide whole section
Featured doctors format gives the feeling that you can shuffle the photos or move through the numbers at the top right ? how can we move through the featured doctors without clicking all doctors ? |  | if we have more than 3 doctors, they are rotating you can add more doctors | It will be hidden | Gouda | hide whole section
“Contact Us” at the bottom, why there is underline CON only ? also is this the email we will use SUPPORT@SECONDMEDICALOPINION.COM Also am not sure we will need a phone number as it will be hard to manage globally without a toll-free |  | Contact us underlined as per the design approved email will be changed with the real mail created and send to us to add it phone number if we don’t need it we will check how can we remove it and make the mail center for example | we will remove phone number | Gouda | Hide Phone number forom homepage contactus section
Will we have the “Interpreters” sign-in at the bottom of the home page ? |  | as per your request before to me | leave it as it is
What is the “blog” , “Trust & Quality “ at the bottom of the home page ? |  | they are inner pages with static text you can send us to add or change these inner pages to other titles with different text | we will remove blog, trust and quality and add TCs | Gouda
I like the YMC shade under the important facts, can we use it as a negative background when possible ? |  | please explain more | Ignore as the control will be removed | Gouda | hide whole section
In the “Doctors” tab, isn’t it a duplication to show the specialties icons and the combo list too ? Also what will appear under the combo box as default when you click the “doctors” tab and before clicking a specialty ? Will it be all doctors photos/cards ? |  | as per the design and yes all doctors appear | remove specialities icons | Gouda | as per image
In the “about us” tab we don’t need to repeat the “Why YMC” again, we should only talk about us as our story | Missing Content | just send us the content you want to add |  | Gouda | Change Why YMC inside aboutus page to our story
The “Help” tab doesn’t have a page to be directed to, it goes again to the “About us” page | CR | missing content to add to inner page |  | Gouda | Create empty page for Help
In the patient sign-in window, the “remember me” check box should be hollow and with the same font not bold pls | Fixed | how hollow? And ok will make it normal text | checkbox background to be white | UI
We need the patient password to show all its criteria at the beginning if the first attempt is wrong, What happens now it shows “ a minimum of 6 characters “ then it shows “Password should contains at least 1 upper character , 1 small character and 1 special character” this should happen in one step. | Fixed | will check |  | UI
The “Terms & Conditions “ in the sign-in/ registration page blue link is not directed to a page with Ts & Cs dummy text | Fixed | will check |  | UI
In the “PATIENT AND FAMILIES REGISTRATION “ -Pls remove families. (remove text) -Can we make the date of birth counters pls (make datepicker) -Can we remove “TV” from “How you heard about us” and add Google Ads., Web also what do you meant by Media(Just change text) | Fixed | will check |  | Gouda | Just Remove Media from patient registeration
After registering, moving to the Ts & Cs page there is no “Accept” button there is “ Next, Ts & Cs” button | Fixed | will check |  | Gouda | Change Next in Registeration Terms and Conditions to be Accept
The rest of the pages after Ts & Cs has the same button of “ Next, Ts & Cs” I think it should only be “NEXT” button | Fixed | will check |  | Fixed
In the mobile/phone number can we allow the “+” sign for international numbers in a separate box or the country code in a separate box to avoid writing with different formats |  | It is better to add country code and it is better to write the telephone without + so in the future if you want to add sms feature it does not get numbers with + , so is that will be ok ? |  | Gouda | add Country Code beside phone
In the credit card page: a. The year format expiry date calendar is in Arabic b. We don’t need the day it is usually month/year format only, so two combo boxes not a calendar with days c. Country/city should be a combo list | Not Started | * no arabic calendars appear can you please provide us with screenshot *ok will change the calendar *no country/city in the credit card page of the case registration |  | Gouda | Add 2 combo boxes with months and years
When I selected the doctor by clicking “Consultation” button it takes me to the “Payment” page, is the payment step one ?!! |  | yes as per your request that the patient will pay first and choose whether he will take the interpreter service or not, at the beginning payment was last step but we changed it based on your request | when the user is not logged in / consultation button to appear | Gouda | Make Consultation Button always appear and if i'm signed out open signin popup
In the “payment” page after consultation, the card expiry date should be a gage month/year | Duplicated to issue no. 24
Step 3 consultation page “ submit medical reports” there is an empty rectangle on the top that is confusing me |  | As per the design so after adding the document it will be added |  | Gouda | Change Upload Control
In the “submit documents “ page -When I drag and drop the documents icons appear on each other so it is not clear whether they are all uploaded or not -I cannot remove a document that I uploaded unless I refresh after I drag it out and drop it -When I uploaded a photo that has a large size it gave me error , so pls we need to specify the size as it is expected to upload photos and when I uploaded a smaller size it went well | Not Started | Will check | we will change the upload control/ how to help the customer minimize the videos to the max. size validated we put file name, change upload control, delete, file size | Gouda | Change Control
After uploading the documents why am I directed to step 1 again “ STEP 1: REQUESTOR AND PATIENT INFORMATION |  | As per the design and business If I am adding data for other person/relative I should add personal information for him | title to be patient information only | Gouda | Patient Information not Requester and patient information
Also this weird note “ If the requestor is not the patient and the patient is over the age of 18, the patient is required to submit a Proxy Consent Form. in order to grant permission to the Cleveland Clinic MyConsult staff in discussing the patient's health information. In the absence of a proxy consent form, our staff is not able to provide any confidential patient information to anyone other than the patient receiving the second opinion. Please Note: Due to State Medical Board restrictions, we are not allowed to offer remote second opinions to patients whose mailing address is in one of the following locations: Guam and North Dakota |  | it was just mentioned in the design so either to replace the text with another one or remove it | remove this note | Gouda
In the “requestor/patient information page a. ” City” only have the same country option. Also why the zip code has up/down arrows button it should be free edited b. Why do we have two stars in the primary phone type title c. Why do we have up/down arrows in the phone fields d. Phone fields do not accept the “+” I suggest separating it by country code list then the number e. The date of birth year is in Arabic and its up/down buttons are not moving when you press and hold also the decrease button is hidden f. Numbers format are not vertically aligned 1970 | Not Started | will check |  | Gouda | 1- Remove arrows from all numbers fields 2-Remove 1 start beside primary phone type 3-Put country code beside phone numbers
In the “ Questionnaire Medical History “ -Do we need the first two options of number 4 ?? also can we change it to “ Medical History Questionnaire “ -Numbers in the height, weight and age are only in Arabic when you use the buttons and only in English when you type them, I suggest remove the buttons pls -Also can we have metric units pls not inches and pounds -Pls remove number 10 “ the patient Ethnic” -Not sure about the format of number 10, contacting my local physician, the boxes should be slim fields | Not Started | will check | remove 1st two options in no. 4 | Gouda -Not sure about the format of number 10, contacting my local physician, the boxes should be slim fields UI | in Patient Registeration Change number fields to be normal textboxes
Number 5, “ Review and Submit “ should show the full form with all data I entered not the price page ! | Not Started | will check |  | Gouda
When I logged out and logged in again -Found the My profile under my log-in name tab at the top left, I think this should more highlighted and clear outside --> needs more explanation -When I clicked my profile didn’t find any data for me or any documents uploaded or even my general profile information --> As per the design of my profile it includes listing for all my consultations but we will implement this -Also on the my profile page, I found a black photo beside my name while there was no option to upload a photo of me in the registration --> from our point of view, for the patient to add photo it will not be useful and we cant control the uploaded photo so we removed it at the adding step and leave it like the black photo, we can talk about this point in the demo if you want to discuss more -In the my profile page the country under my name is in Arabic even if the site is on English --> cant find this can you provide us with screenshot however any content or lookups we can change it with the data provided from your side | Not Started | Please check comments in red |  | UI | we want to add profile page for the doctor and the patient
There was no option as a patient to write a review on a doctor | CR | It was not mentioned before this will be considered as CR |  | Rabab | to check with nevien
As a patient when I clicked on a doctor I found it still saying add the clinical focus while this should appear to the doctor only in his profile page | Not Started | will check |  | Gouda
The name and the photo of the doctors should all be active to click on them not only the price button |  | which part? And please explain more | doctor name and fees should be clickable | Gouda | Make images of doctors wherever in the system to be as link
When I selected a another second doctor after registration a. It didn’t keep my credit card information to select or add a new card information --> this was not mentioned in the design, each time i will enter my data b. It didn’t keep my first name and asked me to enter them again while remembered/recalled the last name --> this for the same purpose of adding someone other than the loggedin person information |  | Please check my comments in red | card number, name? check and get back | Gouda | Ask for saving card information
We need to add a real email of a doctor for the doctor so we can check the rest of the workflow when the doctor receives the request |  | you can register with your personal mail as a doctor and proceed testing | Ignore | Gouda | make card information editable
When I logged in as a patient to see the report coming from the doctor I created it wasn’t clear where to find the report as it appeared on the my profile “ Attached files to see “ !!! also there is no “notifications” tab that should reflect I have a new message !! there is a notification number on the my profile top right corner but it is “0” and am not sure is it the number of cases of the number of notification messages |  | he is receiving email with each step in the case as we agreed before, we just added the notifications for the calls when he requested a call so he can track his calls links on the meeting time | add notification to patient and doctor add email notification when registered want to add newsletter or unsubscribe | Gouda | Send mail t patient after register
When I responded to the doctor, my response didn’t appear as a thread and ALSO it didn’t appear on the doctor’s thread when I re- logged in again as a doctor |  | will check this and get back to you as it is working fine, letus check this in the meeting |  | Gouda | Question Thread Reply not appear and files
In the Physician registration page -The city is changed as the country automatic -There is an “address 1” field only ? -In the upload certification there is an empty rectangle at the beginning with no use as it says drag and drop here while it appears at the top empty rectangle. Also it doesn’t show multiple icons if multiple documents uploaded -The bank information, does it have to be a card only or can be a bank account or what ? -Expiry date of the credit card, same comment as before should be month/year -Can the form smartly detect Master/Visa from the card number -CCV is visible in the card information part -Country field in the payment should be a list -Can the city list also be the cities of the countries selected automatically -I entered a different name on the card data than the doctor’s profile name and it is accepted, can this happen ? do we need a link between all data entries as part of the verification process? -I didn’t fine the Doctor registration number in his own country to verify if this is really a doctor or a spam -In the My profile as a doctor I didn’t have the chance to upload a bio, also I didn’t see it in my profile and it is also not active so I can change it by typing or uploading, also there was no photo of myself to upload -When I clicked edit my data, I had the chance to write the Bio but it wasn’t in the profile creation page, also adding my photo -Edit my profile, when I added a photo it added another box under the photo box not filled the photo box -Also the price and lead time where not labeled so the doctor knows which is which plus they were in Arabic and with up/down arrows that we don’t really need, we also need to fix the currency when we add price or to select between dollars, euros or Sterling -There is a field saying “Add Your main focus of scientific and clinical activity” at the end, didn’t see this at the profile registration , anyways do we need it ? -The response time is written in Hours, pls change to working days -I didn’t see my photo even after I uploaded it while I saw the price and response time -We need to default the stars rating to “zero” till it is changed | Not Started | will check | add job identification number field | Gouda
As a doctor, I registered and found a case from a patient and couldn’t see only one document uploaded |  | you mean you just see one document although you uploaded multiple or what?Please explain more |  | Gouda | Question Thread Reply not appear and files
As a patient or doctor I didn’t get an email notification which should happen in all stages, registration or cases submission |  | It is working and we received emails, just make sure you entered valid mails for doctor and patient and interpreter while registration steps and check the mail at the same time you do the step as we received the mails on the spot
Admin The Admin link gives the below error Server Error in '/' Application. Runtime Error Description: An application error occurred on the server. The current custom error settings for this application prevent the details of the application error from being viewed remotely (for security reasons). It could, however, be viewed by browsers running on the local server machine. Details: To enable the details of this specific error message to be viewable on remote machines, please create a tag within a "web.config" configuration file located in the root directory of the current web application. This tag should then have its "mode" attribute set to "Off". Notes: The current error page you are seeing can be replaced by a custom error page by modifying the "defaultRedirect" attribute of the application's configuration tag to point to a custom error page URL. | Fixed
Remove text boxes below Question number 11 in the patient medical report and leave 1 item only |  |  |  | Gouda

## Comments in calls
Comments | Assigned to
Doctor Bio to allow hyperlink or add another field for online profile | Gouda | Add New Field Online Profile Url
In Physician profile registration: add another address field to have 2 addresses billing address and work address | Gouda
doctors will be deactivated after registartion and then later admin will activate the doctor after offline verification | Gouda | Make default doctor after registeration deactivated
All users will be redirected to their profiles not homepage | Gouda | after signin
Remove price from search on homepage | Gouda | Remove Price DDL from homepage search ctrl
Drop list suggestions when writing in speciality in search textbox | Gouda
Remove specialties listing icons from doctor’s page | duplicated
Icons in why ymc will be not clickable | Gouda | Remove Clickable from icons in this section
Hide Featured doctors and important facts for now | duplicated
In contact us : LinkedIn, twitter, Facebook and Instagram | Gouda | Remove Tembr and G+ and add Instagram
Waiting for countries and cities to fill the lookup | waiting for Customer Reply
Validation message for upload certifications size | Gouda
change upload control to enable uploading multiple attachments once | Gouda | Change control to make direct upload and X button beside each item
Add info icon beside upload certifications to explain the certificates needed | UI | FIXED
In bank information physician registration: we will change card no. to bank account number | Gouda
Mobile no. will be removed from popup registration and added to registration steps | Gouda | Remove Mobile from popup and add to inner page in Registeration of Doctor
text boxes in edit doctor`s profile text for "fees" to be "fees in $" and response time to be "response time in working days" | Gouda | Change place holder in edit doctor profile
Specialty in clinical focus to be focus area | Gouda | Change place holder in edit doctor profile

## Eng. Sameh
Issue Description | Status | Rabab Comment | Customer Comment

## Dr. Wael
Issue Description | Status | Rabab Comment | Customer Comment